## Sheet1
Fix IK elbows Fix sakima walking hand Fix grass color Figure out fire Ensure same lightings
Scene | Shot # | Done | Shot | In | Out | Seconds | Extra | Frames | Notes | fTo-Do
1 | 1 |  | Open - planet (fade) | 0:01 | 0:19 | 17 | 4 | 412 |  | Make planet
| 2 |  | Eye zoom out- walking | 0:19 | 0:26 | 7 | 3 | 171 |  | 1.Retime animation zoom 2. add couple more people
| 3 |  | Overhead | 0:26 | 0:32 | 6 | 0 | 144 |  | Add same amount of people
| 4 |  | Sakima leading | 0:32 | 0:36 | 4 | 13 | 109 |  | Spread people out
| 5 |  | Toy falling out | 0:36 | 0:39 | 2 | 5 | 53
| 6 |  | Toy detail | 0:39 | 0:41 | 2 | 8 | 56
| 7 |  | Colomb misses toy | 0:41 | 0:43 | 1 | 12 | 36 |  | fix Han, look towards fire, retime drop
| 8 |  | Colomb runs to toy | 0:43 | 0:46 | 3 | 4 | 76 |  | Redo Camera, place toy correctly
| 9 |  | Colomb trips | 0:46 | 0:49 | 2 | 16 | 64
| 10 |  | Sakima sees | 0:49 | 0:50 | 1 | 13 | 37 |  | check blendshape render
2 | 1 |  | Establish walking | 0:50 | 0:56 | 5 | 23 | 143 |  | redo camera movement
| 2 |  | Sakima weak | 0:56 | 0:59 | 3 | 2 | 74 |  | zoom in a bit (focal length), add camera movement adjust fall speed extend fire
| 3 |  | Colomb turns and sees | 0:59 | 1:04 | 4 | 23 | 119 |  | Zoom camera in (hide feet turn)
| 4 |  | Colomb helps | 1:04 | 1:08 | 4 | 3 | 99 |  | extend fire, fix lean animation
| 5 |  | laying zoom out | 1:08 | 1:14 | 5 | 22 | 142
3 | 1 |  | Sakima Stressed | 1:14 | 1:20 | 6 | 2 | 146
| 2 |  | Colomb looking | 1:21 | 1:24 | 3 | 2 | 74
| 3 |  | Sakima leaves | 1:24 | 1:27 | 2 | 22 | 70
| 4 |  | Sakima looking (side) | 1:27 | 1:30 | 3 | 0 | 72
| 5 |  | Sakima walking (rear) | 1:30 | 1:36 | 6 | 2 | 146
| 6 |  | Colomb watching (side) | 1:36 | 1:39 | 3 | 0 | 72
0
4 | 1 |  | POV from compass to colomb | 1:39 | 1:42 | 2 | 22 | 70
| 2 |  | POV compass | 1:42 | 1:45 | 2 | 21 | 69 |  | redo hand movement
| 3 |  | Colomb | 1:45 | 1:54 | 9 | 6 | 222 | 1:47:00 (frame 48) Look up 1:50:00 (frame 120) start walking
| 4 |  | Earth | 1:54 | 2:03 | 9 | 3 | 219
Scene 5: fix eyes
5 | 1 |  | Bridge Establish | 2:03 | 2:08 | 5 | 5 | 125 |  | Fix people floating Fix fire
| 2 |  | Urging people to cross | 2:08 | 2:13 | 4 | 14 | 110
| 3 |  | Looking across bridge | 2:13 | 2:15 | 2 | 5 | 53
| 4 |  | Look back to people and leave | 2:15 | 2:18 | 2 | 23 | 71 | 2:16:18 (frame 23) turn
| 5 |  | Overhead of fire encroaching | 2:18 | 2:21 | 2 | 22 | 70
| 6 |  | People pushed to bridge | 2:21 | 2:24 | 3 | 2 | 74 |  | Fix floating people
| 7 |  | Rope catches fire | 2:24 | 2:30 | 5 | 7 | 127
| 8 |  | Fire across bridge | 2:30 | 2:33 | 2 | 23 | 71
| 9 |  | OTS Colomb, bridge falls | 2:33 | 2:36 | 2 | 22 | 70 | 2:33:22 (frame 18) bridge falls | Fix bridge blendshape random floating eyes
| 10 |  | Colomb distraught | 2:36 | 2:38 | 2 | 7 | 55 |  | fix colomb blendshape
Scene 6: redo animations
6 | 1 |  | Fade in, looking at tree | 2:40 | 2:42 | 2 | 20 | 68
| 2 |  | OTS, looking up to trees | 2:43 | 2:45 | 2 | 22 | 70
| 3 |  | Feel tree | 2:45 | 2:52 | 6 | 4 | 148
| 4 |  | Climbing Trees | 2:52 | 2:57 | 5 | 0 | 120
| 5 |  | In tree - looking at characters | 2:57 | 3:02 | 5 | 0 | 120
| 6 |  | In tree- looking down | 3:02 | 3:07 | 5 | 0 | 120
| 7 |  | World - fade out | 3:07 | 3:21 | 14 | 9 | 345